## Log
HTTP > HTTPS Conversion Checklist http://www.domainname.com/
Document History
V1.0 - 03/08/17 - First iteration of the document.
V1.1 - 03/29/17 - Added warning about Let's Encrypt

## Task List
HTTP -> HTTPS Migration Checklist
No. | Category / Task |  | Who | When | Status | Comment
SETUP
1 |  | Setup staging environment (or backup site).
2 |  | Scan site using Screaming Frog or another scanning tool. Note and resolve any redirect chains. Check canonical tag content - is it being used? Note external file references. These are ones we may need to update; embedded content and CDN references, for example. Keep a copy of the scan.
3 |  | Note social share counts.
4 |  | Choose and purchase the appropriate SSL certificate. Make sure it covers the root and subdomain, multiple sites if you're using a CDN. From a rankings point of view, it makes absolutely no difference what type of certificate you use. (For now.)
WEBSITE
5 |  | Install certificate.
6 |  | Update all hardcoded links to https. Don't use the Really Simple SSL plugin cause it's a temporary solution, meaning it works dynamically and does not update the database. Use Better Search Replace instead. Change http://mydomain.com to https://mydomain.com AND http://www.mydomain.com to https://www.mydomain.com (no regex). Don't forget about hard-coded widgets (like feedburner).
7 |  | Update canonicals (unless Better Search Replace or another WP plugin has done the job for you). Some sites are hard-coded.
8 |  | Update references in templates, for example, forms. Search and replace may have gotten them all but sample to be sure.
9 |  | Update custom JS, AJAX libraries to https. If you're using a CDN, change those settings in, for example, BWP Minify.
10 |  | Add 301 redirects at the server level. See Redirection Scripts Tab(below) for specific instructions for nginx and apache. Check with your hosting company. They may do this for you when you request (and they install) the certificate.
11 |  | Update robots.txt file to fix any hard-coded references (if any) to http (for example, sitemap).
12 |  | Enable the HSTS response header. This tells the browser to always use HTTPS, which eliminates a server-side check and makes your website load faster. This can also cause confusion at times, since the redirect will show as 307. It could have a 301 or a 302 behind it, though, and you may need to clear your browser cache to see which. Like #10 above, your hosting company may do this for you.
13 |  | Enable OCSP stapling. This enables a server to check if a security certificate is revoked instead of a browser, which keeps the browser from having to download or cross-reference with the issuing certificate authority. Like #s 10 and 12 above, your hosting company may do this for you.
14 |  | Update domain registrar. Not all registrars require this. You should check.
YOAST
15 |  | Deactivate and reactivate Yoast. This will ensure the sitemap gets properly updated.
CDN
16 |  | Intall SSL certificate on CDN.
17 |  | Update original URL on CDN.
18 |  | Enable http/2 support of CDN.
19 |  | Update all hardcoded CDN links to https.
ANALYTICS
20 |  | Update GSC (add site, sitemap, fetch and ask to be reindexed). Don't forget to ask for any important pages not linked to the home page to be indexed separately. You do not need to notify Google of a 'change of address". Keep both versions of the sitemap in place for one month, then remove the http one. If you are using URLs parameters, the existing configuration should be replicated in the HTTPs site profile
21 |  | Provide disavow file to the new GSC https enabled version of the site.
22 |  | Update GA profile. If necessary, update your analytics tracking code. Most modern Google Analytics tracking snippets already handle HTTPS, but older code may need a second look.
EXTERNAL LINKS
23 |  | Update significant external online references, for example, Adwords, social media accounts, Google and Bing maps.
24 |  | Update significant external offline references, for example, signature files, job fair and trade show materials, letterhead, etc.
25 |  | Migrate social share counts. These counts do NOT impact your rankings (as far as we know) but they act as strong social proof, and it's frustrating to migrate a page with thousands of tweets and likes only to see them reset to zeros. Some social networks (Facebook, Google+, LinkedIn) will transfer counts through their APIs, but it could take weeks or months for them to display correctly. (See how-to article below.) I'm finding as more time passes, there's less need to worry about this as social share tools are getting on the bandwagon and doing this for you. But, as a minimum, BASELINE AND MONITOR.
26 |  | Update any paid media, email or marketing automation campaigns to use the HTTPS versions of the URLs.
27 |  | Update any other tools such as A/B testing software, heatmaps and keyword tracking to use the HTTPS versions of the URLs.
RSS FEED
28 |  | Many sites still use FeedBurner for RSS feeds. Unfortunately, Google stopped supporting it long ago and FeedBurner isn't compatible with HTTPS. If you use FeedBurner, you'll need to migrate your RSS to an HTTPS-compatible service. If you're technically competent you can do this yourself, or FeedPress has a very inexpensive RSS migration solution.
TESTING
29 |  | View the site. Everything look as expected?
30 |  | Confirm Wordpress Settings > General uses https
31 |  | Check hreflang tags (if used).
32 |  | Check internal site search to make sure it's working and referencing https.
33 |  | Intall SSL certificate on CDN.
34 |  | Look at the Yoast-generated sitemap to make sure it's recording https versions of URLs.
35 |  | Scan site using Screaming Frog or another scanning tool. Note and resolve any new redirect chains. Check canonical tag content - is it being used? Note external file references. Have these been updated?
36 |  | Check social share counts. Are they as expected? It may take a few days.
37 |  | Monitor GSC to ensure all pages get indexed and there are no errors. Check 1, 2 and 4 weeks out.
38 |  | Check, double-check and triple-check to make sure everything is as it should be. There are so many places where things can go wrong.
Reference Articles:
1 |  | Collection of Articles - https://www.pinterest.com/beseenontop/website-migrations-and-seo/
2 |  | Lets Encrypt - https://www.wordfence.com/blog/2017/03/chrome-secure/
3 |  | HSTS - https://en.wikipedia.org/wiki/HTTP_Strict_Transport_Security?__hstc=103427807.aa37f3c262f91a91eef68b2d547bb30e.1488475341389.1488475341389.1488478370637.2&__hssc=103427807.1.1488478370637&__hsfp=1969369558
4 |  | FeedPress - https://feed.press/feedburner-alternative?__hstc=103427807.aa37f3c262f91a91eef68b2d547bb30e.1488475341389.1488475341389.1488478370637.2&__hssc=103427807.1.1488478370637&__hsfp=1969369558
5 |  | Preserve Social Shares - https://searchenginewatch.com/sew/how-to/2172926/maintain-social-shares-site-migration
Tools:
1 |  | https://www.jitbit.com/sslcheck/
2 |  | https://www.whynopadlock.com/
3 |  | https://www.screamingfrog.co.uk/seo-spider/
4 |  | https://www.ssllabs.com/ssltest/
5 |  | https://www.htbridge.com/ssl/
6 |  | To view information about a site’s certificate, you can open up Chrome’s developer tools and view the security tab. You can do this by going to the View > Developer > Developer Tools menu.
7 |  | https://www.htbridge.com/ssl/
8 |  | https://yoast.com/moving-your-website-to-https-ssl-tips-tricks/

## Redirection Scripts
This information was supplied by Godaddy - https://www.godaddy.com/help/redirect-http-to-https-automatically-8828

## External Files
URL